## 01_Executive_Summary
JVH-FSM ¦ PROJECT DELIVERY & GOVERNANCE
Package 3 ¦ Design gate status and controlled delivery plan ¦ v1.0
DESIGN GATE: ON TRACK WITH CONTROLLED WATCH ITEMS
Area | Status | Evidence / Reason | Management Action
Scope | ON TRACK | Package 2 baseline approved; Release 1 exclusions unchanged. | Protect route-tool/technical boundary through change control.
Schedule | ON TRACK | Design Approved 2026-10-16; configuration phase starts 2026-10-19. | Protect UAT exit and blackout; monitor dependency slippage.
Requirements / Design | ON TRACK | 39 functional + 13 NFR; 33 business rules; 23 fit-gap items; 31 config items. | Begin CONFIG/BUILD and configuration validation.
Data | WATCH | Migration boundary approved; source profiling, consent/contact and inventory freshness evidence not yet executed. | Start inventory/profiling weeks 6-9.
Interfaces | WATCH | 8 interface designs complete; exact retained-system methods remain validation items. | Validate methods early; use governed-file fallback if needed.
Mobile / Identity | WATCH | Weak-signal queued behavior and office SSO product fit remain open. | Validate during config/UAT; preserve named-account/fallback controls.
Resources | ON TRACK | Detailed phase effort and primary/delegate coverage planned within charter ranges. | Confirm gate attendance; escalate missed critical participation.
NEXT 14 DAYS: configure intake/readiness + validate interface methods + begin source inventory/profiling + draft test strategy
Decision / Risk | State | Owner | Next action
CR-001 Route tool replacement | DEFER TO PHASE 2 | Operations Sponsor | Keep INT-002/003; no Release 1 scope change
RISK-002 Interface fit | WATCH | System Administrator | Validate CRM/route/QBO/gateway methods by week 8
RISK-004 Consent/contact | WATCH | Customer Service Lead | Profile in Package 4 before UAT entry
RISK-009 Mobile weak signal | WATCH | Field Supervisor | Field test / UAT scenario before UAT entry

## 02_Phase_Plan
PHASES, DATES & FORMAL GATES
The sixteen delivery weeks are controlled by evidence-based gates while workstreams overlap whenever dependencies permit
Phase ID | Phase | Start Week | End Week | Calendar Start | Calendar End | Formal Gate
PH-01 | Initiation & Discovery | 1 | 2 | 2026-09-14 | 2026-09-25 | Discovery Complete
PH-02 | Requirements & Solution Design | 3 | 5 | 2026-09-28 | 2026-10-16 | Design Approved
PH-03 | Configuration, Data & Interface Preparation | 6 | 9 | 2026-10-19 | 2026-11-13 | Configuration Baseline
PH-04 | Validation & Data Migration | 10 | 11 | 2026-11-16 | 2026-11-27 | UAT Entry
PH-05 | UAT & Defect Resolution | 12 | 13 | 2026-11-30 | 2026-12-11 | UAT Exit
PH-06 | Training & Readiness | 14 | 14 | 2026-12-14 | 2026-12-18 | Training Ready
PH-BLK | Year-End Change Blackout |  |  | 2026-12-21 | 2027-01-01 | No Production Change
PH-07 | Cutover & Go-Live Readiness | 15 | 15 | 2027-01-04 | 2027-01-08 | Go-Live Ready
PH-08 | Go-Live, Hypercare & Handoff | 16 | 16 | 2027-01-11 | 2027-01-22 | Hypercare Exit

## 03_Weekly_Roadmap
WEEKLY DELIVERY ROADMAP
Workstreams deliberately overlap: data, interfaces, test, change, training, cutover and support start before their peak execution phases
Week | Start | End | Primary Work | Controlled Overlap / Early Work | Gate / Outcome | Status
1 | 2026-09-14 | 2026-09-18 | Kickoff, stakeholder confirmation, intake/dispatch discovery | Start data/source inventory; identify reporting questions | Discovery working | Complete
2 | 2026-09-21 | 2026-09-25 | Systems/data/field discovery; playback; current-state confirmation | Begin interface/access questions; early test/change planning | Discovery Complete | Complete
3 | 2026-09-28 | 2026-10-02 | Objectives/KPI definitions; business rules; requirements drafting | Data attributes and reporting events identified | Design working | Complete
4 | 2026-10-05 | 2026-10-09 | Requirements prioritization; fit-gap; access/interface design | Testability review; training impacts identified | Design working | Complete
5 | 2026-10-12 | 2026-10-16 | Functional solution design; configuration spec; design playback | Interface/data risks and validation queue finalized | Design Approved | Complete
6 | 2026-10-19 | 2026-10-23 | Configure intake/readiness/roles; interface technical review | Data inventory/profiling starts; test strategy drafting | Configuration working | Planned
7 | 2026-10-26 | 2026-10-30 | Configure scheduling, capacity, and exceptions; design reviews | Mapping/cleansing rules; UAT scenario design | Configuration working | Planned
8 | 2026-11-02 | 2026-11-06 | Configure field/closeout/follow-up/inventory; access review | Mock exchange files; training-needs analysis | Configuration working | Planned
9 | 2026-11-09 | 2026-11-13 | Configuration validation; baseline candidate; interface checks | Migration validation readiness; UAT data prep | Configuration Baseline | Planned
10 | 2026-11-16 | 2026-11-20 | Migration validation, reconciliation, and interface validation | Finalize test data; UAT entry evidence | Validation working | Planned
11 | 2026-11-23 | 2026-11-27 | Correct data/config exceptions; UAT entry review | Cutover/support planning updated | UAT Entry | Planned
12 | 2026-11-30 | 2026-12-04 | UAT cycle 1; defect triage; high-risk regression planning | Training content updates from UAT | UAT working | Planned
13 | 2026-12-07 | 2026-12-11 | Retest/regression; UAT exit evidence | Readiness issues translated into training/support actions | UAT Exit | Planned
14 | 2026-12-14 | 2026-12-18 | Train-the-trainer; role competency; access/readiness review | Cutover rehearsal preparation; KB finalization | Training Ready | Planned
15 | 2027-01-04 | 2027-01-08 | Final data/load plan; cutover rehearsal; go/no-go package | Support activation; communications; freeze | Go-Live Ready | Planned
16 | 2027-01-11 | 2027-01-15 | Go-live, smoke test, daily hypercare triage | Knowledge/support updates | Production live | Planned
16.2 | 2027-01-18 | 2027-01-22 | Hypercare stabilization; issue ownership; support handoff | Benefits-measurement setup | Hypercare Exit | Planned

## 04_Workstream_Plan
DETAILED WORKSTREAM PLAN
Tasks connect completed discovery/design evidence to configuration, data, validation, UAT, readiness, cutover and support
Plan ID | Workstream | Activity | Start | Finish | Owner | Dependencies | Output / Gate Evidence | Status
PLN-001 | Governance | Confirm role-based sponsor/business/process/data/test/training ownership | 2026-09-14 | 2026-09-18 | Implementation Lead | ART-001/002 | Governance baseline | Complete
PLN-002 | Discovery | Run role-based discovery and current-state playback | 2026-09-14 | 2026-09-24 | Business Analyst | PLN-001 | Package 1 findings/process | Complete
PLN-003 | Design | Govern KPI definitions and value hypotheses | 2026-09-28 | 2026-10-02 | Operations Manager | PLN-002 | KPI dictionary | Complete
PLN-004 | Design | Define business rules and decision tables | 2026-09-28 | 2026-10-09 | Business Analyst | PLN-002 | Rules catalog | Complete
PLN-005 | Design | Approve functional/nonfunctional requirements and priorities | 2026-09-28 | 2026-10-09 | Operations Manager | PLN-003; PLN-004 | 39 FR / 13 NFR baseline | Complete
PLN-006 | Design | Perform vendor-neutral fit-gap and technical-boundary review | 2026-10-05 | 2026-10-14 | Implementation Lead | PLN-005 | 23 fit-gap dispositions | Complete
PLN-007 | Design | Define configuration, role/access and state model | 2026-10-05 | 2026-10-14 | System Administrator | PLN-005; PLN-006 | 31 config items; permission matrix | Complete
PLN-008 | Design | Define retained-system interfaces and open technical validations | 2026-10-05 | 2026-10-14 | System Administrator | PLN-006 | 8 interface designs | Complete
PLN-009 | Design | Conduct design playback and role-based design approval | 2026-10-16 | 2026-10-16 | Operations Manager | PLN-003 to PLN-008 | Design Approved gate | Complete
PLN-010 | Configuration | Configure intake/readiness/priority and request states | 2026-10-19 | 2026-10-23 | System Administrator | PLN-009 | CONFIG baseline subset | Not Started
PLN-011 | Configuration | Configure eligibility/capacity/publication/override controls | 2026-10-26 | 2026-10-30 | System Administrator | PLN-009 | Scheduling config subset | Not Started
PLN-012 | Configuration | Configure exceptions, field closeout and quality review | 2026-11-02 | 2026-11-06 | System Administrator | PLN-009 | Field/exception config subset | Not Started
PLN-013 | Configuration | Configure inventory readiness and follow-up/SLA rules | 2026-11-02 | 2026-11-06 | System Administrator | PLN-009 | Inventory/SLA config subset | Not Started
PLN-014 | Access | Configure roles/permissions and validate named-account lifecycle | 2026-10-26 | 2026-11-06 | System Administrator | PLN-007 | Access baseline | Not Started
PLN-015 | Interfaces | Validate CRM, route tool, QBO and messaging exchange methods | 2026-10-19 | 2026-11-06 | System Administrator | PLN-008 | Interface method dispositions | Not Started
PLN-016 | Data | Inventory sources and map active/open migration objects | 2026-10-19 | 2026-10-30 | Data Owner | PLN-005; PLN-008 | Data inventory/mapping | Not Started
PLN-017 | Data | Profile/clean source extracts including consent/contact and inventory freshness | 2026-10-26 | 2026-11-13 | Data Owner | PLN-016 | Quality/cleansing evidence | Not Started
PLN-018 | Configuration | Validate configured baseline and disposition gaps | 2026-11-09 | 2026-11-13 | Implementation Lead | PLN-010 to PLN-015 | Configuration Baseline gate | Not Started
PLN-019 | Testing | Draft test strategy and requirement-based UAT scenarios | 2026-10-26 | 2026-11-20 | Test Lead | PLN-005; PLN-006 | Test strategy / UAT pack | Not Started
PLN-020 | Data | Run migration validation and reconcile eligible records | 2026-11-16 | 2026-11-25 | Data Owner | PLN-017; PLN-018 | Mock load/reconciliation | Not Started
PLN-021 | Interfaces | Execute controlled interface validation with failure paths | 2026-11-16 | 2026-11-25 | System Administrator | PLN-015; PLN-018 | Interface validation evidence | Not Started
PLN-022 | Testing | Assemble UAT entry evidence and approve tester/data readiness | 2026-11-25 | 2026-11-27 | Test Lead | PLN-019 to PLN-021 | UAT Entry gate | Not Started
PLN-023 | UAT | Execute UAT cycle 1 and log defects | 2026-11-30 | 2026-12-04 | Test Lead | PLN-022 | UAT results / defects | Not Started
PLN-024 | UAT | Retest resolved defects and run targeted regression | 2026-12-07 | 2026-12-10 | Test Lead | PLN-023 | Retest/regression evidence | Not Started
PLN-025 | UAT | Review UAT exit and critical acceptance disposition | 2026-12-11 | 2026-12-11 | Operations Manager | PLN-023; PLN-024 | UAT Exit gate | Not Started
PLN-026 | Change/Training | Complete role impact/training needs and finalize quick guides | 2026-11-02 | 2026-12-11 | Training Lead | PLN-007; UAT feedback | Training package | Not Started
PLN-027 | Training | Train lead users and validate role competency | 2026-12-14 | 2026-12-17 | Training Lead | PLN-025; PLN-026 | Training/competency evidence | Not Started
PLN-028 | Readiness | Review access, training, defects, data, support and cutover readiness | 2026-12-18 | 2026-12-18 | Operations Manager | PLN-025; PLN-027 | Training Ready gate | Not Started
PLN-029 | Cutover | Run cutover rehearsal and close rehearsal gaps | 2027-01-04 | 2027-01-06 | Implementation Lead | PLN-028 | Rehearsal evidence | Not Started
PLN-030 | Cutover | Assemble GO / CONDITIONAL GO / NO-GO decision package | 2027-01-07 | 2027-01-08 | Implementation Lead | PLN-029 | Go-Live Ready gate | Not Started
PLN-031 | Launch | Execute approved production promotion and smoke test | 2027-01-11 | 2027-01-11 | System Administrator | PLN-030 | Smoke-test evidence | Not Started
PLN-032 | Hypercare | Run daily triage, disposition production issues and update knowledge | 2027-01-11 | 2027-01-22 | Support Lead | PLN-031 | Hypercare log / KB updates | Not Started
PLN-033 | Handoff | Transfer configuration, support ownership and unresolved lower-severity items | 2027-01-21 | 2027-01-22 | System Administrator | PLN-032 | Support handoff / Hypercare Exit | Not Started

## 05_Resource_Plan
ROLE EFFORT & CRITICAL RESOURCE PLAN
Effort models delivery feasibility without rates, fees, invoices or fabricated commercial budget
Role / Group | Phase ID | Phase | Phase Weeks | Avg Hours / Week | Planned Person-Hours | Control Note | Phase | Planned Person-Hours
Implementation Lead | PH-01 | Initiation & Discovery | 2 | 28 | 56 | Scenario planning allocation; no commercial rate | Initiation & Discovery | 100
Implementation Lead | PH-02 | Requirements & Solution Design | 3 | 30 | 90 | Scenario planning allocation; no commercial rate | Requirements & Solution Design | 216
Implementation Lead | PH-03 | Configuration, Data & Interface Preparation | 4 | 30 | 120 | Scenario planning allocation; no commercial rate | Configuration, Data & Interface Preparation | 332
Implementation Lead | PH-04 | Validation & Data Migration | 2 | 34 | 68 | Scenario planning allocation; no commercial rate | Validation & Data Migration | 174
Implementation Lead | PH-05 | UAT & Defect Resolution | 2 | 38 | 76 | Scenario planning allocation; no commercial rate | UAT & Defect Resolution | 192
Implementation Lead | PH-06 | Training & Readiness | 1 | 30 | 30 | Scenario planning allocation; no commercial rate | Training & Readiness | 78
Implementation Lead | PH-07 | Cutover & Go-Live Readiness | 1 | 38 | 38 | Scenario planning allocation; no commercial rate | Cutover & Go-Live Readiness | 88
Implementation Lead | PH-08 | Go-Live, Hypercare & Handoff | 2 | 36 | 72 | Scenario planning allocation; no commercial rate | Go-Live, Hypercare & Handoff | 154
Operations Sponsor | PH-01 | Initiation & Discovery | 2 | 2 | 4 | Scenario planning allocation; no commercial rate
Operations Sponsor | PH-02 | Requirements & Solution Design | 3 | 2 | 6 | Scenario planning allocation; no commercial rate
Operations Sponsor | PH-03 | Configuration, Data & Interface Preparation | 4 | 1 | 4 | Scenario planning allocation; no commercial rate
Operations Sponsor | PH-04 | Validation & Data Migration | 2 | 1 | 2 | Scenario planning allocation; no commercial rate | Validation & Data Migration
Operations Sponsor | PH-05 | UAT & Defect Resolution | 2 | 2 | 4 | Scenario planning allocation; no commercial rate
Operations Sponsor | PH-06 | Training & Readiness | 1 | 2 | 2 | Scenario planning allocation; no commercial rate
Operations Sponsor | PH-07 | Cutover & Go-Live Readiness | 1 | 4 | 4 | Scenario planning allocation; no commercial rate
Operations Sponsor | PH-08 | Go-Live, Hypercare & Handoff | 2 | 2 | 4 | Scenario planning allocation; no commercial rate
Operations Manager | PH-01 | Initiation & Discovery | 2 | 6 | 12 | Scenario planning allocation; no commercial rate
Operations Manager | PH-02 | Requirements & Solution Design | 3 | 10 | 30 | Scenario planning allocation; no commercial rate
Operations Manager | PH-03 | Configuration, Data & Interface Preparation | 4 | 8 | 32 | Scenario planning allocation; no commercial rate
Operations Manager | PH-04 | Validation & Data Migration | 2 | 8 | 16 | Scenario planning allocation; no commercial rate | Validation & Data Migration
Operations Manager | PH-05 | UAT & Defect Resolution | 2 | 12 | 24 | Scenario planning allocation; no commercial rate
Operations Manager | PH-06 | Training & Readiness | 1 | 12 | 12 | Scenario planning allocation; no commercial rate
Operations Manager | PH-07 | Cutover & Go-Live Readiness | 1 | 10 | 10 | Scenario planning allocation; no commercial rate
Operations Manager | PH-08 | Go-Live, Hypercare & Handoff | 2 | 8 | 16 | Scenario planning allocation; no commercial rate
System Admin / Data Owners | PH-01 | Initiation & Discovery | 2 | 4 | 8 | Scenario planning allocation; no commercial rate
System Admin / Data Owners | PH-02 | Requirements & Solution Design | 3 | 8 | 24 | Scenario planning allocation; no commercial rate
System Admin / Data Owners | PH-03 | Configuration, Data & Interface Preparation | 4 | 14 | 56 | Scenario planning allocation; no commercial rate
System Admin / Data Owners | PH-04 | Validation & Data Migration | 2 | 16 | 32 | Scenario planning allocation; no commercial rate | Validation & Data Migration
System Admin / Data Owners | PH-05 | UAT & Defect Resolution | 2 | 14 | 28 | Scenario planning allocation; no commercial rate
System Admin / Data Owners | PH-06 | Training & Readiness | 1 | 10 | 10 | Scenario planning allocation; no commercial rate
System Admin / Data Owners | PH-07 | Cutover & Go-Live Readiness | 1 | 16 | 16 | Scenario planning allocation; no commercial rate
System Admin / Data Owners | PH-08 | Go-Live, Hypercare & Handoff | 2 | 14 | 28 | Scenario planning allocation; no commercial rate
Operational Leads / SMEs | PH-01 | Initiation & Discovery | 2 | 6 | 12 | Scenario planning allocation; no commercial rate
Operational Leads / SMEs | PH-02 | Requirements & Solution Design | 3 | 8 | 24 | Scenario planning allocation; no commercial rate
Operational Leads / SMEs | PH-03 | Configuration, Data & Interface Preparation | 4 | 6 | 24 | Scenario planning allocation; no commercial rate
Operational Leads / SMEs | PH-04 | Validation & Data Migration | 2 | 4 | 8 | Scenario planning allocation; no commercial rate | Validation & Data Migration
Operational Leads / SMEs | PH-05 | UAT & Defect Resolution | 2 | 8 | 16 | Scenario planning allocation; no commercial rate
Operational Leads / SMEs | PH-06 | Training & Readiness | 1 | 8 | 8 | Scenario planning allocation; no commercial rate
Operational Leads / SMEs | PH-07 | Cutover & Go-Live Readiness | 1 | 4 | 4 | Scenario planning allocation; no commercial rate
Operational Leads / SMEs | PH-08 | Go-Live, Hypercare & Handoff | 2 | 5 | 10 | Scenario planning allocation; no commercial rate
Vendor Consultant | PH-01 | Initiation & Discovery | 2 | 4 | 8 | Scenario planning allocation; no commercial rate
Vendor Consultant | PH-02 | Requirements & Solution Design | 3 | 12 | 36 | Scenario planning allocation; no commercial rate
Vendor Consultant | PH-03 | Configuration, Data & Interface Preparation | 4 | 20 | 80 | Scenario planning allocation; no commercial rate
Vendor Consultant | PH-04 | Validation & Data Migration | 2 | 18 | 36 | Scenario planning allocation; no commercial rate | Validation & Data Migration
Vendor Consultant | PH-05 | UAT & Defect Resolution | 2 | 12 | 24 | Scenario planning allocation; no commercial rate
Vendor Consultant | PH-06 | Training & Readiness | 1 | 6 | 6 | Scenario planning allocation; no commercial rate
Vendor Consultant | PH-07 | Cutover & Go-Live Readiness | 1 | 12 | 12 | Scenario planning allocation; no commercial rate
Vendor Consultant | PH-08 | Go-Live, Hypercare & Handoff | 2 | 8 | 16 | Scenario planning allocation; no commercial rate
Lead Testers / Trainers | PH-01 | Initiation & Discovery | 2 | 0 | 0 | Scenario planning allocation; no commercial rate
Lead Testers / Trainers | PH-02 | Requirements & Solution Design | 3 | 2 | 6 | Scenario planning allocation; no commercial rate
Lead Testers / Trainers | PH-03 | Configuration, Data & Interface Preparation | 4 | 4 | 16 | Scenario planning allocation; no commercial rate
Lead Testers / Trainers | PH-04 | Validation & Data Migration | 2 | 6 | 12 | Scenario planning allocation; no commercial rate | Validation & Data Migration
Lead Testers / Trainers | PH-05 | UAT & Defect Resolution | 2 | 10 | 20 | Scenario planning allocation; no commercial rate
Lead Testers / Trainers | PH-06 | Training & Readiness | 1 | 10 | 10 | Scenario planning allocation; no commercial rate
Lead Testers / Trainers | PH-07 | Cutover & Go-Live Readiness | 1 | 4 | 4 | Scenario planning allocation; no commercial rate
Lead Testers / Trainers | PH-08 | Go-Live, Hypercare & Handoff | 2 | 4 | 8 | Scenario planning allocation; no commercial rate
Role / Group | Planned Person-Hours | Charter Planning Boundary | Review
Implementation Lead | 550 | 24-32 hr/week typical; 32-40 peak | Within charter-level planning range; exact named-person schedule not represented
Operations Sponsor | 30 | 1-2 hr/week; 2-4 hr/gate peak | Within charter-level planning range; exact named-person schedule not represented
Operations Manager | 152 | 4-6 hr/week typical; 8-12 peak | Within charter-level planning range; exact named-person schedule not represented
System Admin / Data Owners | 202 | 6-10 hr/week typical; 12-16 peak | Within charter-level planning range; exact named-person schedule not represented
Operational Leads / SMEs | 106 | 2-4 hr/week typical; 6-8 peak | Within charter-level planning range; exact named-person schedule not represented
Vendor Consultant | 218 | 8-16 hr/week typical; 16-24 peak | Within charter-level planning range; exact named-person schedule not represented
Lead Testers / Trainers | 76 | 2-4 hr/week prep; 6-10 peak | Within charter-level planning range; exact named-person schedule not represented

## 06_RACI
RESPONSIBILITY / RACI MATRIX
A=accountable; R=responsible; C=consulted; I=informed. The Implementation Lead coordinates delivery evidence; business acceptance and launch approval remain with the designated owners.
Deliverable / Decision | Operations Sponsor | Operations Manager | Implementation Lead | Dispatch Lead | Customer Service Lead | Field Supervisor | System Administrator | Data Owner | Vendor Consultant | Finance Owner | Training/Test Leads
Requirements / business rules | C | A | R | C | C | C | C | I | I | I
Configuration design | I | C | R | C | C | C | A/R | C | C | I | I
Configuration build | I | C | C | C | C | I | A/R | C | R | I | I
Data mapping / profiling | I | C | C | C | C | C | A | R | C | C | I
Interface design / validation | I | C | C | C | I | I | A/R | C | R | C | I
UAT strategy / execution | I | A | C | R | R | R | C | C | C | I | C
Defect disposition | I | A | R | C | C | C | R | C | C | I | C
Training needs / materials | I | A | C | C | C | C | C | I | C | I | R
Cutover plan / rehearsal | A | C | R | C | C | C | R | R | C | C | C
GO / CONDITIONAL GO / NO-GO | A | C | R | I | I | I | C | C | C | I | I
Hypercare / support handoff | I | A | R | C | C | C | R | C | C | I | C

## 07_RAID
RAID - ACTIVE RISK CONTROL
Risks retain consequence, owner, response and source control; unresolved assumptions remain distinct from proven issues
Risk ID | Category | Risk / Consequence | Impact | Probability | Rating | Owner | Response / Mitigation | Status | Related Control
RISK-001 | Data | Late source-data ownership or poor data quality delays mapping, migration validation, or UAT entry. | High | Medium | High | Operations Manager | Start inventory/profiling during configuration; name owners/due dates; keep critical reconciliation gate. | OPEN | ASM-013; Package 4
RISK-002 | Interfaces | A required retained-system connector is unsupported or behaves differently than the scenario design. | High | Medium | High | System Administrator | Validate methods early; use governed structured-file fallback; route material impact through change control. | OPEN | ASM-007 / DEC-025
RISK-003 | Resources | SME/tester/trainer unavailability weakens decisions, UAT or readiness and may move gates. | High | Medium | High | Operations Sponsor | Role-based primary + delegate coverage; protect gate sessions; escalate missed critical participation. | MITIGATED | ASM-017 / Package 3 resource plan
RISK-004 | Customer Communications | Consent/contact quality constrains automated SMS activation. | High | Medium | High | Customer Service Lead | Profile consent/contact early; keep channel eligibility gate; maintain manual fallback. | OPEN | ASM-014 / DEC-027
RISK-005 | Schedule | Defects or data exceptions compress the pre-blackout readiness window. | High | Medium | High | Implementation Lead | Protect UAT exit, training readiness and blackout; use evidence-based go/no-go rather than calendar pressure. | OPEN | ASM-011
RISK-006 | Adoption | Role readiness or support capacity is insufficient for independent production access. | High | Medium | High | Operations Manager | Link access to training/competency; train lead users; activate support plan before go-live. | OPEN | ASM-012
RISK-007 | Dispatch Usability | Capacity/readiness controls generate too many warnings and slow high-volume dispatch. | Medium | Medium | Medium | Dispatch Lead | Use OPEN/NEAR LIMIT/OVER; reserve hard blocks for true readiness failures; usability UAT with dispatch leads. | OPEN | DEC-021/022
RISK-008 | Inventory | Stale inventory data creates false HOLDs or misses material readiness risk. | High | Medium | High | Inventory Coordinator | Display source freshness; stale state routes to review; validate source freshness in Package 4. | OPEN | REQ-INV-005
RISK-009 | Mobile | Weak-signal behavior differs from expected queued-update design and disrupts status/closeout. | High | Medium | High | Field Supervisor | Validate supported offline/queued actions; visible sync state; documented fallback; field UAT. | OPEN | ASM-010
RISK-010 | Accounting | Completed-work handoff creates duplicate/rejected QBO transactions or weak reconciliation. | High | Low | Medium | Finance Owner | Unique external reference; rejected-row queue; control-total reconciliation; targeted interface UAT. | OPEN | DEC-028 / INT-004
RISK-011 | Security | Role configuration grants excessive rights or offboarding leaves unnecessary access. | High | Low | Medium | System Administrator | Least-privilege matrix; named accounts; access review before readiness; termination/offboarding test. | OPEN | ASM-009 / NFR-006/007
RISK-012 | Scope | Pressure to replace the retained route tool adds unvalidated route-optimization scope during configuration. | Medium | Medium | Medium | Operations Sponsor | Use CR-001 impact analysis; preserve current scope and defer route-tool replacement to Phase 2 unless formally rebaselined. | CONTROLLED | CR-001

## 08_Gate_Register
FORMAL GATE REGISTER
Gates represent evidence disposition by accountable roles, not ceremonial milestone completion
Gate | Scenario Date | Accountable Role | Minimum Evidence | State | Control Note
Discovery Complete | 2026-09-25 | Operations Manager | Current-state/process evidence; open-question ownership; discovery playback | COMPLETE | Package 1 accepted
Design Approved | 2026-10-16 | Operations Manager | KPI/rules/requirements; fit-gap; solution; configuration spec; access/interface intent | COMPLETE | Package 2 accepted; controlled technical/data validations remain
Configuration Baseline | 2026-11-13 | Operations Manager + System Administrator | Configured baseline; config validation; access baseline; interface method disposition; open gaps controlled | PLANNED | Cannot close from specification alone
UAT Entry | 2026-11-27 | Test Lead + Operations Manager | Configuration/data/interface validation; mock load/reconciliation; test data; entry blockers disposed | PLANNED | Evidence driven
UAT Exit | 2026-12-11 | Operations Manager | Critical/Must-Have acceptance disposed; >=90% overall; no undisposed critical failure | PLANNED | GL-001 to GL-004
Training Ready | 2026-12-18 | Operations Manager | Role training/competency; access validation; support readiness | PLANNED | Independent access only for ready users
Go-Live Ready | 2027-01-08 | Operations Sponsor | UAT/data/training/access/release/cutover/support/contingency evidence | PLANNED | GO / CONDITIONAL GO / NO-GO package
Hypercare Exit | 2027-01-22 | Operations Manager | Production stability; issue ownership; knowledge updates; support/config handoff | PLANNED | Unresolved lower-severity items retain owner/target

## 09_Communications
COMMUNICATION & MEETING CADENCE
Cadence activates when lifecycle need exists; daily triage is not imposed throughout the project
Meeting / Communication | Cadence | Default Scenario Time | Participants | Decision / Purpose | Owner | Record / Output
Weekly Project Status & Decision Review | Weekly | Mon 09:00 | Operations Sponsor; Operations Manager; Implementation Lead; workstream leads | Overall status, decision needs, RAID changes, milestone/gate health | Implementation Lead | Executive status + action/decision log
Design / Configuration Working Session | 2x weekly during weeks 3-9 | Tue/Thu 13:00 | Operations Manager; Dispatch/CSR/Field leads; System Admin; Vendor Consultant | Rules, requirements, configuration, and design decisions | Implementation Lead | Decision/configuration updates
Data & Interface Working Session | Weekly weeks 6-11 | Wed 10:00 | System Admin; Data Owner; Finance; Customer Service; Vendor Consultant | Source ownership, mapping, quality, interface methods, failure/reconciliation controls | System Administrator | Data/interface action log
UAT Readiness / Triage | Daily during weeks 12-13 | 15:30 | Test Lead; Implementation Lead; System Admin; process leads | Test results, defects, blockers, retest and targeted regression | Test Lead | Defect/UAT disposition
Training & Readiness Review | 2x during week 14 | Tue/Thu 14:00 | Operations Manager; Training Lead; process leads; System Admin | Competency, access, support and readiness exceptions | Training Lead | Readiness evidence/actions
Formal Gate Review | At each major gate | Scheduled gate slot | Accountable gate role; Implementation Lead; relevant owners | Evidence review and formal role-based disposition | Implementation Lead | Gate decision record
Cutover Command Review | Daily week 15 + go-live day | 08:30 | Operations Sponsor; Operations Manager; Implementation Lead; System Admin; Support Lead | Rehearsal gaps, cutover readiness, communications, contingency | Implementation Lead | Cutover/go-no-go record
Hypercare Standup | Daily first 5 production days; 3x second week | 09:00 | Operations Manager; Support Lead; System Admin; process leads | Production issues, impact, workaround, owner, SLA and knowledge updates | Support Lead | Hypercare log / KB

## 10_Change_Control
CHANGE CONTROL - CR-001
A plausible scope request is impact-assessed rather than silently absorbed; the Release 1 baseline remains unchanged
Field | Controlled Record
Change Request ID | CR-001
Scenario request date | 2026-10-19
Requested by | Dispatch Lead / Operations Manager
Request | Replace the retained Route Planning Tool in Release 1 and add native automated route optimization inside the target FSM.
Business rationale | Remove route-tool exchange/reconciliation and reduce duplicate operational handling.
Current approved boundary | Route Planning Tool remains retained; Target FSM exchanges approved assignments/sequence through supported connector or governed file. Custom route-optimization algorithm development is out of scope.
Requirements / design affected | INT-002; INT-003; NFR-011; route publication design; dispatcher workflow; interface testing; training; cutover.
Technical impact | Requires proof of proprietary/native optimization fit or new algorithm capability. Custom algorithm/middleware development would violate the Release 1 technical boundary.
Schedule impact | Would add discovery/fit-gap, configuration, data/interface testing and UAT work during weeks 6-13, increasing risk to the year-end blackout and 2027-01-11 target.
Data impact | Adds route-optimization inputs, constraint data and new result/reconciliation requirements not in the approved migration/interface baseline.
Training / change impact | Dispatcher workflow, troubleshooting, route exception handling and support materials would materially change.
Risk impact | Increases RISK-002, RISK-005 and creates product-fit dependency for a capability explicitly excluded from Release 1.
Options considered | A) approve now and rebaseline; B) evaluate only standard native feature if it can replace the retained tool with no new material scope; C) keep retained route tool in Release 1 and evaluate replacement in Phase 2.
Recommendation | C - keep retained route tool in Release 1 and add route-tool replacement/optimization evaluation to Phase 2 backlog.
Decision owner | Operations Sponsor
Disposition | DEFERRED TO PHASE 2 / RELEASE 1 SCOPE UNCHANGED
Decision date | 2026-10-21
Downstream action | Keep INT-002/003 validation in Package 2/5; add route-tool replacement evaluation to closure/Phase 2 backlog; no change to Release 1 configuration baseline.
Impact Area | Assessment | Release 1 Effect | Disposition
Scope | Material expansion | Would alter explicit route-tool/optimization exclusion | Do not absorb
Schedule | High risk | Adds work during config/UAT and threatens blackout/readiness | Avoid
Technical | Unverified capability | May require proprietary fit or custom engineering | Phase 2 discovery
Data/Test | Material | New route constraints/results, test cases and reconciliation | Phase 2
Training/Support | Material | Dispatcher troubleshooting and support model changes | Phase 2

## 11_Decision_Register
ACTIVE DECISION REGISTER
Material design and change decisions remain visible to downstream implementation, test and readiness work
ID | Decision | Status | Decision Owner | Source
DEC-021 | Capacity state thresholds | Approved | Operations Manager | Package 2
DEC-022 | Route publication blockers | Approved | Operations Sponsor | Package 2
DEC-023 | Selective critical inventory | Approved | Operations Manager | Package 2
DEC-024 | Follow-up SLA tiers | Approved | Operations Manager | Package 2
DEC-025 | Connector-first/file-fallback interfaces | Approved | System Administrator | Package 2
DEC-026 | Named accounts + office SSO where supported | Approved | System Administrator | Package 2
DEC-027 | Consent-gated SMS activation | Approved | Customer Service Lead | Package 2
DEC-028 | Controlled QuickBooks handoff | Approved | Finance Owner | Package 2
CR-001 | Retain route tool in Release 1; defer replacement/optimization | Deferred to Phase 2 | Operations Sponsor | Package 3 change control

## 12_Package_Gate
PACKAGE 3 ACCEPTANCE
Project planning is ready to manage delivery. Configuration, data, validation, training, and launch decisions remain tied to their project gates.
Acceptance Dimension | Disposition | Evidence | Accountable Role
Detailed overlapping plan | MET | 33 plan activities from discovery through hypercare; controlled overlap explicitly modeled | Implementation Lead
Milestones and formal gates | MET | 8 formal readiness gates plus blackout window | Operations Sponsor
RACI / decision authority | MET | Role-based RACI keeps business approval separate from delivery coordination | Operations Manager
Resource feasibility | MET | Phase effort fits charter planning ranges; no rates/pricing modeled | Operations Sponsor
RAID / escalation | MET | 12 active risks with owner/response; no fabricated issue closure | Implementation Lead
Communication cadence | MET | Lifecycle-appropriate status, working, gate, UAT and hypercare cadences | Implementation Lead
Change control | MET | CR-001 impact assessed and deferred to Phase 2; Release 1 scope unchanged | Operations Sponsor
Package 4 readiness | MET WITH WATCH ITEMS | Requirements/data definitions stable; source quality, consent and inventory freshness are Package 4 evidence | Data Owner

## 99_Lists
Task Status | Risk Status | Gate State | RACI | Exec Status | Impact
Not Started | OPEN | PLANNED | R | ON TRACK | High
In Progress | MITIGATED | COMPLETE | A | WATCH | Medium
Complete | CONTROLLED | AT RISK | C | AT RISK | Low
At Risk | CLOSED | NO-GO | I | CRITICAL
Deferred | ESCALATED